## Gantt Chart
GANTT CHART: DSI Project 4
* = an automatically calculated cell
| TASK NAME | START DATE | END DATE | START ON DAY* | DURATION* (WORK DAYS) | TEAM MEMBER(S) | PERCENT COMPLETE | WEEK 1 | WEEK 2
DSI Project 4: Predicting The Presence of West Nile Virus
| Read project requirements | 2021-11-08 | 2021-11-08 | 0 | 1 | All | 100%
| Discuss project requirements | 2021-11-09 | 2021-11-09 | 1 | 1 | All | 100%
| Preliminary data cleaning | 2021-11-09 | 2021-11-11 | 1 | 3 | All | 100%
| Discuss data cleaning steps | 2021-11-11 | 2021-11-11 | 3 | 1 | All | 100%
| Refine data cleaning notebook | 2021-11-11 | 2021-11-12 | 3 | 2 | Shi Min, Huimin, Haziq | 100%
| General EDA | 2021-11-13 | 2021-11-15 | 5 | 3 | All | 100%
| Explore heatmaps | 2021-11-13 | 2021-11-15 | 5 | 3 | Shu Kai, Saloni | 100%
| Discuss EDA | 2021-11-15 | 2021-11-15 | 7 | 1 | All | 100%
| Clean up EDA notebook | 2021-11-15 | 2021-11-16 | 7 | 2 | Huimin, Shi Min | 100%
| Modeling | 2021-11-15 | 2021-11-18 | 7 | 4 | Haziq, Shu Kai | 100%
| Discuss modeling results | 2021-11-18 | 2021-11-18 | 10 | 1 | All | 100%
| Readme | 2021-11-18 | 2021-11-18 | 10 | 1 | Saloni | 100%
| Slides and final notebooks | 2021-11-18 | 2021-11-18 | 10 | 1 | All | 100%
| Project submission and presentation | 2021-11-19 | 2021-11-19 | 11 | 1 | All | 100%
Formulas:
DURATION* (WORK DAYS) = DATEDIF([START DATE],[END DATE],"d")+1